## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Instructions
| Table 1 | Instructions
Test Plan
| Table 1 | Test Plan

## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-261-05-g GForce
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a customer, I want to add and remove products from my cart so that I can choose what to purchase. | Given a user shopping cart, when a customer adds a product, then they expect to see an updated cart with the new product. | Pass | AC, ANC, RS; 10/10/22 | Pass | ANC; 11/07/22
| Given a user shopping cart, when a customer removes a product, then they expect to see an updated cart without the deleted product. | Pass | AC, ANC, RS; 10/10/22 | Pass | ANC; 11/07/22
As an owner, I want to add, edit, and remove products from the inventory so that I can change what is being sold on the E-Store. | Given a product inventory, when an owner adds a product, then they expect to see an updated inventory with the new product. | Pass | JD, RT, AC; 10/12/22 | Pass | ANC; 11/07/22
| Given a product inventory, when an owner edits a product, then they expect to see updated information for that product. | Pass | JD, RT, AC; 10/12/22 | Pass | ANC; 11/07/22
| Given a product inventory, when an owner removes a product, then they expect to see an updated inventory without the deleted product. | Pass | JD, RT, AC; 10/12/22 | Pass | ANC; 11/07/22
As a user, I want to search for a product so that I can find the product I am looking for. | Given a search bar, when a user enters text into the text field, then they see the relevant search results appear on the web page. | Pass | JD, RT, AC, ANC; 10/12/22 | Pass | ANC; 11/07/22
As a user, I want to log into my account so that I can access my information. | Given a login button, when a user clicks it, then they see a login pop-up page. | Pass | ANC, AC, RT; 10/10/22 | Pass | ANC; 11/07/22
| Given a login page, when a user enters and submits their information, then they see an updated page with their information. | Pass | ANC, AC, RT; 10/10/22 | Pass | ANC; 11/07/22
As a customer, I want to checkout my cart items so that I can purchase and confirm my order. | Given a shopping cart, when a customer clicks on the checkout button, then they are redirected to a checkout screen. |  |  | Pass | ANC; 11/07/22
| Given a checkout screen, when a customer clicks on the “Confirm Order” button, then they see an “Order Confirmed” message. |  |  | Pass | ANC; 11/07/22
As a user, I want to view the E-Store in a dark mode so that I can view the webpage without hurting my eyes. | Given a webpage, when a user views it, then they see that there is a darker background with text color changes. |  |  | Pass | ANC; 11/07/22
As a customer, I want to receive and use coupons so that I can get discounts on products. | Given a coupon notification, when a customer views it, then they see that they have received a new coupon they can use. |  |  | Pass | ANC; 11/07/22
| Given a checkout screen, when a customer clicks on the “Apply coupon” button, then they see the discount applied to their order. |  |  | Pass | ANC; 11/07/22
As an owner, I want to add, edit, and remove users from the database. | Given a user management webpage, when an owner adds a new user, then they see a new listing for that user. |  |  | Pass | TA, GB 11/3/22 says username taken when trying to add a new user. ANC; 11/07/22
| Given a user management webpage, when an owner removes a user, then they see the listing for that user disappear. |  |  | Pass | TA, GB 11/3/22 user deleted from ui when x button pressed ANC; 11/07/22
| Given a user management webpage, when an owner edits an existing user’s information, then they see the new info displayed for the user. |  |  | Pass | TA, GB 11/3/22 ANC; 11/07/22
|  |  |  | Pass | GB 11/3/22 let admin change username to a taken username ANC; 11/07/22
radio buttons for users instead of typing in true or false
Having a capital 'E' in my username broke everything
I murdered pepper pot by trying to make a user
multiple failures trying to delete users
+ and - buttons in the shopping cart allow addition of items into cart past what is currently in the inventory